ERP Project Delivery Schedule (4 Stages — 5‑Month Plan)

This document outlines the professional 4‑stage delivery schedule for the ERP system. Stage 1 (Figma Design) is already completed. The remaining 3 stages span a total timeline of approximately 5 months.

Stage 1 — Figma UX/UI Design (Completed)

Duration: 2–3 weeks (Already Completed)

Deliverables:

• Finalized UI/UX screens for all ERP modules.

• Design system and component library.

• User flows and clickable prototypes.

Stage 2 — Core Backend, Database & API Development

Timeline: Month 1 → Month 2 (Approx. 8 Weeks)

Objectives:

- Implement backend services for all ERP modules: Item/BOM, Purchase, Inventory, Production, QMS, OEE, Finance.

- Build PostgreSQL schema and migrations.

- Develop REST APIs, validations, and business rules.

- Implement RBAC and authentication.

Deliverables:

• Complete set of backend APIs.

• Database schema + seed data.

• API documentation (OpenAPI).

• Unit and integration tests.

Stage 3 — Cloud Deployment, On‑Prem Setup & Hybrid Sync

Timeline: Month 2 (end) → Month 3 → Mid‑Month 4 (Approx. 6 Weeks)

Objectives:

- Deploy ERP backend to AWS (VPC, ECS, RDS, ECR, API Gateway, S3).

- Deploy ERP frontend to S3 or CloudFront.

- Configure on‑prem server (Ubuntu, Docker, PostgreSQL).

- Establish VPN tunnel between office and AWS.

- Configure AWS DMS for full load + CDC sync.

- Validate offline mode + automatic resync.

Deliverables:

• Cloud ERP environment operational.

• On‑prem ERP instance running.

• Hybrid sync fully tested.

• CI/CD pipelines for deployments.

Stage 4 — QA, UAT, Training & Final Project Delivery (Go‑Live)

Timeline: Mid‑Month 4 → Month 5 (Approx. 6 Weeks)

Objectives:

- System integration testing across all ERP modules.

- Performance and security testing.

- User Acceptance Testing with client teams.

- Training sessions for department users.

- Preparation of SOPs and user manuals.

- Final go‑live and hypercare support.

Deliverables:

• UAT sign‑off.

• Production deployment.

• Training documentation + videos.

• Final project handover package.

## Summary Timeline (5 Months)

• Stage 1 (Completed): Figma UI/UX — 2–3 weeks

• Stage 2: Backend & API Development — Months 1–2

• Stage 3: Cloud + On‑Prem + DMS Sync — Month 2 (end) to Mid‑Month 4

• Stage 4: QA, UAT & Go‑Live — Mid‑Month 4 to Month 5

## Sign‑Off

Client Representative: ___________________________   Date: ____________

Vendor Representative: __________________________   Date: ____________